## ProjectTeam
Name | GitHub Alias
Mauro Tschanz | tschm2
Maurice Zysset | zyssm4
Kaspar Schmocker | schmk3
Rea Iseli | iselr1
Philippe Noser | nosep2

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Create Infopage | The User enters all relevant Data about himself and his disease | high | 20 |  | 0h | waiting
2 | Enter a new drug | The user can enter the name and dosage he has to take, afterwards he has a overview of all drugs he has to take a day | medium | 70 |  | 0h | waiting
3 | new Appointment | The User makes a new Appointment with the doctor | high | 50 |  | 0h | waiting
|  |  | Total | 120

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Package Structure | Create Packages and structures |  | nosep2/schmk3 | zyssm4 | high | 1 | 1 | 1 | closed
1.2 | 1 | Infopage View | Create the GUI | UI | zyssm4 | tschm2 | high | 6 | 10 | 7 | in Progress
1.3 | 1 | Login View | Create the GUI | UI | tschm2 | iselr1 | high | 6 | 6 | 5 | in Progress
1.4 | 1 | Create Person, Patient, Doctor, Relatives Class | Create the Classes | Class | schmk3 | nosep2 | high | 3 | 3 | 4 | closed
1.4 | 1 | Infopage Logic | Create the logic of the infopage, Write to File and Read from File | controller | iselr1 | schmk3 | high | 4 | 7 | 6 | in Progress
1.5 | 1 | View Navigator Vaadin | Create a Navigater to change the views | UI | tschm2 | zyssm4 | medium | 4 | 5 | 5 | in Progress
1.6 | 1 | login gui | create the gui | UI | nosep2 | tschm2/iselr1 | low | 5 | 5 | 4 | in Progress
1.7 | 1 | Loginveiw to Navigator | Add Loginview to the Navigator | Login | tschm2/iselr1 | nosep2 | low | 1 | 1 | 1 | closed
1.8 | 1 | Login Validators | Create Validators for Pasword and Username(Temporary Solution) | Login | iselr1 | tschm2 | low | 1 | 2 | 2 | closed
1.9 | 2 | Bug Fixing UserManager | Fix SaveInfopage |  | iselr1 |  |  | 1 | 1 | 1 | closed
1.11 | 2
1.12 | 2 | Exception Handling Infopage | Handling of the Exception during reading the Data | InfoPage | iselr1 |  | high | 1 | 1 | 1 | closed
in Progress
2.1 | 2 | Medication View | Create the GUI | UI | schmk3 |  | high | 8 |  | 6 | in Progress
2.2 | 2 | Medication UI Element | Medication Element for creating new drugs | controller | tschm2/zyssm4 |  | high | 26 | 17 |  | in Progress
2.3 | 2 | Medication Loader | Loads saved Medications | controller | zyssm4 |  | Medium | 2 |  |  | in Progress
2.4 | 2 | Medication Saver | Save the Medications | controller | nosep2 |  |  | 2 |  |  | in Progress
2.5 | 2 | State pattern | State Medication | Medication | tschm2/zyssm4 |  | Medium | 25 |  |  | in Progress
2.6 | 2 | Login Validators | Recreate the Validator Logic with an TextFile reader | Login | iselr1 |  | high | 4 | 3 | 2 | in Progress
[7 empty] | total | 100 | 62 | 45

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180